## Lapas1
DATE | WORK ACHIEVED | WORK TO BE ACHIEVED
2020-11-29 | Uploaded all the datasets into Google Drive and decided to use Pytorch library for the project | Find a suitable platform to load the datasets in
2020-11-30 | Decided to use Google Colab for the project. Loaded the datasets in Google Colab platform. Analysed the datasets (image resolution, size, their names) and also grouped them by names. | Do research on Pytorch. Start applying some machine learning techniques on the images and prepare for algorithm implementations.